UFO V2 Migration

Initial Project Review & Migration Scope

Current-State Assessment, Target Architecture, and Phased Plan

Workstream:

TechRequest V2 data migration · PySpark transform modernization · TypeScript Functions V2 upgrade

Target Platform:

Palantir Foundry — Code Repositories, Ontology Manager, Workshop

Document Owner: Solution Architecture · Date: 12 May 2026 · Version: 0.1 (Draft)

# Table of Contents

# 1. Executive Summary

UFO (Unified Field-Service Operations) is a Palantir Foundry application supporting the triage, prioritization, and closure of TechRequest dossiers across the Airbus operator network. The current platform comprises a PySpark data-transformation repository that builds the operational object set, and a TypeScript V1 ontology-functions repository that powers prioritization, FSR workflows, comment management, escalations, and reporting.

Airbus has released TechRequest V2 — a re-shaped, snake_case data contract that expands dossier coverage with post-treatment, interruption, manufacturing-quality, and richer requestor-company attributes. In parallel, Foundry has shipped Functions V2 (TypeScript), Ontology SDK v2 patterns, and incremental-transform best practices. UFO must migrate to remain on a supported tool-chain and to absorb the new business signals.

This document establishes the current-state baseline, defines the migration scope, identifies risk, and proposes a phased plan. It is the input to the detailed architecture and design specifications that will follow.

## 1.1 Goals

- Adopt the V2 TechRequest data contract end-to-end across the data pipeline and ontology surface.

- Re-platform the PySpark transforms onto incremental, schema-typed, declarative pipelines that meet enterprise traffic and SLA expectations.

- Upgrade the Ontology Functions repository to Functions V2 (TypeScript) with stronger typing, better testability, and ontology-edit ergonomics.

- Re-design ontology object types, links, and actions to reflect the V2 model and expose post-treatment, interruption, and manufacturing-quality concerns first-class.

- Produce API-grade documentation for every transform, function, object type, link type, and action type.

## 1.2 Non-Goals (this phase)

- Re-implementing the Workshop dashboards — these will be migrated only where ontology field renames force it.

- Changes to Skywise integration contracts upstream of TechRequest V2.

- Re-platforming to Python-Functions or AIP-agent workflows — both are tracked as Phase 3 follow-ons.

## 1.3 Top-Line Recommendations

- Adopt a snake_case canonical model. Stop mirroring Foundry property mangling in PySpark; let the Ontology Manager handle display names. This eliminates dozens of brittle string mappings.

- Replace row-by-row Python collect() loops with native PySpark DataFrame APIs. The current UFOEntries job collects the entire driver dataset and re-iterates per row — it will not scale to V2 volumes.

- Split the monolithic MyFunctions class. Today everything from prioritization to escalations sits in index.ts. Refactor by domain (Prioritization, Escalation, Linking, Reporting) under Functions V2.

- Introduce a TechRequest interface. An Ontology Interface lets shared properties (dossier_id, ata, operator_code_icao) be reused across UfoEntry, message, approval doc, and post-treatment object types.

- Make incrementality first-class. Switch from full snapshot transforms to incremental + APPEND with primary keys, so V2 volume growth doesn't compound compute spend.

# 2. Project Inventory

The working tree under UFO_V2/ contains three first-class assets: the input data, the data-transformation repository, and the ontology-functions repository. A documentation directory provides the operator-facing user guides describing the existing UFO workflow.

## 2.1 Directory Layout

| Path | Purpose | Owner |
| --- | --- | --- |
| Data/ | Sample CSVs of V1 inputs (RDAFSample, MessageSmallSample, UFO_ApprovalDocuments…), V1 outputs (icaoUFOobjects, UFOPath, MessagesKPI, RTSbyMSN), and the new V2 inputs (techrequest_index_metadata_v2, tr_dossier_metadata_filtered, tr_messages_metadata, tr_manufacturing_quality_reference, tr_linked_dossier). | Data Engineering |
| DataTransformationRepository/ | PySpark transforms (ApprDoc.py, ICAOObjects.py, MessageParsing.py, NicoTest.py, UFOEntries.py, UFOPath.py) that build the operational Foundry datasets backing the ontology. | Data Engineering |
| UFO_OntologyObject_Functions/ | TypeScript V1 ontology functions: prioritization (index.ts/MyFunctions), FSR utilities (FSRFunctions.ts, fsrTeam.ts), comments (Comments.ts, commentUsersDictionary.ts), reporting (reportGenerator.ts), state-machine scaffolding (PathSupp.ts), restoration helpers (restoration.ts), and miscellany (Misc.ts). | Software Engineering |
| Documentation/ | PDF user-guides describing Create Request, Internal Requestor flow, Analyse_Request, Provide_contribution, Approve Doc variants (RDAF, ASAC, FCD), Defect_Report, Contribution_RDTS, Send Final Answer, Visibility, plus the UFO Part-by-Part reference. | Product / FSR Team |

## 2.2 PySpark Transform Map

Each transform writes to a fixed dataset RID. The output of UFOEntries is the spine of the ontology — it is the source for the UfoEntry object type.

| Transform | Inputs (V1 RIDs / Columns) | Outputs | Notes |
| --- | --- | --- | --- |
| UFOEntries.py | source_df at ri.foundry.main.dataset.5699f900… — V1 dossier index with columns like dossierLabel, operatorICAOCode, msn[], approval_doc_type, dossUpdateDate. | outputData (Ufoentry rows) and rtsData (MSN→RTS dictionary). | Builds the UfoEntry skeleton. Currently performs collect()+for-loop, custom schemaSet, and string-scraping RTS dates from free-text labels. |
| MessageParsing.py | Foundry message dataset ri.foundry.main.dataset.8fa6145d… — messageStatus, messageFrom_partnerType, messageTitle, messageCreationDate. | MessagesKPI output dataset. | Filters open / recent messages, classifies as Permanent Request and Damage Report via title keyword search. |
| UFOPath.py | messages (output of MessageParsing) + appr (output of ApprDoc). | UFOPath dataset with RDAF + Instruction delivery status by dossier. | Uses module-level dossSeen* dictionaries — not safe for incremental runs. |
| ApprDoc.py | rdaf dataset + message dataset (V1 attachments). | Approval-doc consolidated dataset feeding the UFOPath state machine. | Derives limitation-life percentage from free-text 'limitation_type'. |
| ICAOObjects.py | UFOEntries output. | ICAO summary dataset with OPEN / Closed / Amber / Red counts (initialized at zero). | Mostly a template generator; counts are populated by the calculateCountsforICAOS() ontology function. |
| NicoTest.py | Same A320 dataset as MessageParsing. | Per-ICAO A320 counts. | Appears experimental / one-shot; review for removal. |

## 2.3 TypeScript Ontology Functions Map

| Module | Responsibility | Key Functions |
| --- | --- | --- |
| index.ts (MyFunctions) | Prioritization driver, FSR-edit driver, escalation handling, stored-action batch driver, ICAO count calc, shared-property propagation. | priorityDriver, calculateOneEntryScore, fsrEntryDriver, escalate, deEscalate, createEscalationObject, batchDriver, setSharedProperties. |
| FSRFunctions.ts | FSR identity lifecycle and favorites. | scanandDelete (1-year inactivity), scenarioFSRMatch + scenarioDriverandReturnFSRFav, addAndupdateFSRFavs, removeAndupdateFSRFavs. |
| fsrTeam.ts | FSR team-membership rollups. | setTeamMembers. |
| Comments.ts | Parsing, formatting, and routing of comment strings stored on UfoEntry/FsrTeam. | newCommentBreakdownhelper, linkedCommentcounter, addCommentstoUFOEntry, updateLinkedComments, custSuppComments, partsComments, technicalComments, plus most-recent-comment maps. |
| commentUsersDictionary.ts | UUID → display-name dictionary for tagging mentions. | commentUsers Record<string,string>. |
| reportGenerator.ts | Daily escalation digest email + comment rollup. | reportDriver, getEscalations, getComments, formatComments, getActions. |
| restoration.ts | Workshop dashboard filter-state diff helpers. | filterChange, returnRestoredList. |
| PathSupp.ts | Commented-out state-machine scaffolding for the dossier path object. | (currently disabled). |
| Misc.ts | FSR comment-flag toggle plus commented experimental helpers. | commentFlag. |

# 3. V1 → V2 Data Contract Shift

Comparison of the two TechRequest contracts (V1 mixed-case / camelCase vs V2 snake_case) drives every downstream change. Naming is not just cosmetic — it is the deepest source of churn in the existing pipeline because every PySpark loop and every TypeScript switch statement hard-codes V1 property names.

## 3.1 Headline Differences

- Naming convention. V1 uses camelCase / mixed-case (operatorICAOCode, dossierTitle, id_dossier). V2 is consistently snake_case (operator_code_icao, dossier_title, dossier_id).

- Identifier rename. id_dossier → dossier_id; id_aircraft → manufacturer_aircraft_id; msn → aircraft_msn; ata_4d → ata; dossierClosureDate → closure_time + closure_time_tz.

- Timezone-explicit timestamps. V2 splits every datetime into a value column plus a *_tz column. The PySpark transforms must be reworked to parse the offset and store a single TimestampType (UTC) — keeping the offset only where needed for display.

- Richer dossier metadata. tr_dossier_metadata_filtered adds dossier-chargeable status and reason, AMM / IPC / TSM references, topic_code & sub_topic_code taxonomies, full requestor-company profile (icao, cki, cage, category, country), and full post-treatment block (SARI, TDO, manufacturing-quality, environment impact, ISI, doc-content).

- Operational-interruption signals. is_operational_interruption, is_technical_interruption, interruption_duration / type / symptom code, ETOPS/EDTO flag, departure & arrival airports, main base, maintenance action, validation, sent-to-ecollection. These deserve their own object type.

- New auxiliary feeds. tr_manufacturing_quality_reference (Skywise RFI links) and tr_linked_dossier (Move/Copy parent-child links between dossiers) — both are first-class relationships that should become ontology Link Types.

## 3.2 Field Mapping (Selected Dossier Columns)

| V1 Column (input + PySpark schemaSet) | V2 Column | Type Change / Notes |
| --- | --- | --- |
| id_dossier / Dossier_ID | dossier_id | Same content. Rename only. Becomes Ontology primary key for UfoEntry. |
| dossier_internal_id / Internal_Id | dossier_internal_id | Unchanged. Keep as alternate key for Skywise traceability. |
| dossierTitle / Title | dossier_title | Rename. Continue to use for keyword scoring. |
| dossierLabel / Label | dossier_label | Rename. Keep RTS-from-label scraper but plan to deprecate when V2 surfaces a structured RTS. |
| operatorICAOCode / operator_ICAO | operator_code_icao | Rename. The PySpark 'USA → AAL' patch must move into a reference table, not be hard-coded. |
| msn (Array) | aircraft_msn (Array) | Rename. V2 keeps array semantics for multi-MSN dossiers. |
| ataChapter / ata_4d | ata_chapter / ata | ata_4d → ata. ata_chapter retained. ata_section and ata_paragraph become first-class in tr_dossier_metadata_filtered. |
| dossUpdateDate / dossSubmitDate / dossierClosureDate | update_time + update_time_tz / submit_time + submit_time_tz / closure_time + closure_time_tz | Type change: two columns per timestamp. Parse to UTC TimestampType in the bronze layer. |
| approval_doc_type | approval_doc_type | Same. Keep RDAF/TD parsing. |
| dossier_chargeable / dossier_chargeable_reason / amm_reference / ipc_reference / tsm_reference | (new in V2) | Surface as UfoEntry properties; useful for prioritization and triage. |
| topic_code / topic_code_description / sub_topic_code / sub_topic_code_description | (new in V2) | Promote to a Topic / SubTopic taxonomy in the ontology (consider a Value Type-backed enum). |
| requestor_company_code_icao / _code_cki / _cage_code / _category / _country / _arp_list_id | (new in V2) | Either join into a Company object type with a reference link, or store as denormalized properties for query speed. |
| post_treatment_status / _reason / _required / _sari / _tdo / _manufacturing_quality / _environment_impact / _isi / _doc_content (all subfields) | (new in V2) | Becomes a sibling object type PostTreatment with a 1-to-1 link to UfoEntry. |
| is_operational_interruption / is_technical_interruption / interruption_* / departure_airport_iata / arrival_airport_iata | (new in V2) | Becomes Interruption object type with optional 1-to-1 link to UfoEntry. |

## 3.3 Auxiliary Feeds

tr_messages_metadata replaces the V1 message dataset. It introduces explicit message_id (formerly id_message), message_internal_id, message_type / message_sub_type (e.g., Information, Acknowledgement), message_visibility, planned-answer / requested-answer timestamps with explicit TZ, urgency, message_label, quotation_* metadata, and skywise_solution_deliverable_id.

tr_manufacturing_quality_reference (skywise_rfi_id → dossier_id, dossier_internal_id, rfi_message_id, rfi_creation_time + tz) is the manufacturing-quality RFI registry. This becomes the source for a ManufacturingQualityRfi object type linked to UfoEntry.

tr_linked_dossier (skywise_link_id, dossier_id, dossier_internal_id, linked_dossier_id, linked_dossier_internal_id, linked_type ∈ {Move, Copy, …}) feeds a new Ontology Link Type — a many-to-many between UfoEntry objects representing dossier lineage.

# 4. Current-State Pain Points

## 4.1 Data Pipeline

- Row-by-row Python in driver code. UFOEntries.py collects the entire source DataFrame to the driver and iterates with Python for-loops. This pattern voids Catalyst optimization, defeats partition parallelism, and will not survive V2 volumes.

- Module-level mutable state. msnSeen, dossSeenMessages, dossSeenRDAFs, dossSeenInstr are top-level dictionaries that accumulate state across rows. They make the transforms non-deterministic under incremental execution and impossible to reason about in distributed workers.

- Hardcoded dataset RIDs. Each @transform pins ri.foundry.main.dataset.<uuid> directly. V2 needs a parameterized layout (bronze/silver/gold) so dev/test branches can swap inputs without code edits.

- Free-text field scraping. scrapeRTS, altenESGITDCheck, permReq, damageReport, and the limitation()-life calculator all attempt to recover structure from free-text titles and labels. V2 introduces structured topic_code, sub_topic_code, post_treatment_*, and interruption_* fields that make most of this obsolete.

- Schema duplication. schemaSetGen() functions hand-write 60+ StructFields per transform. Any drift between Foundry property names, the PySpark schema, and the TS function switch-statements has caused outages historically.

- No incrementality. Every run rebuilds the entire dataset. Foundry supports @incremental + APPEND with primary keys; V2 should adopt it.

## 4.2 Ontology Functions

- Monolithic MyFunctions. index.ts is ~1,350 lines: prioritization, FSR edits, ICAO counts, shared-property pulls, escalation lifecycle, and stored-action replay all coexist. Hard to test, hard to deprecate, hard to evolve.

- Manual property pulls. configureAlgorithm() repeats the same param-config block ten times for parameters 1–10. The whole prioritization config could be table-driven with a few lines of TypeScript.

- Switch-statement key mappings. getPriorityValsForOneEntry() is a 270-line switch that translates Foundry property keys into entry values. A typed property descriptor map (keyof Ufoentry) and a single accessor would eliminate it.

- Stringly-typed inter-function contracts. Comments, stored-actions, and FSR escalations are encoded into delimited strings (%* , '.', '-'). Functions V2 supports first-class structs — promote them to ontology Struct types.

- Disabled / commented code. PathSupp.ts, large blocks in Misc.ts, and several in-line comments contain commented-out experiments. Salvage what's reusable; delete the rest.

- FSR favorites are scalar arrays. UfoFsr.favorites is a string[] of dossier_ids. This is what Link Types exist for — a many-to-many UfoFsr ↔ UfoEntry link gives O(1) joins, indexing, and Workshop filterability.

# 5. Target Architecture

## 5.1 Data Pipeline — Bronze / Silver / Gold

Re-organize the DataTransformationRepository around a medallion pattern. Each layer has clear inputs, outputs, and SLAs. All transforms become declarative or PySpark-native (no driver-side Python loops).

| Layer | Purpose | Examples |
| --- | --- | --- |
| Bronze | Raw V2 ingest, schema-enforced, TZ-normalized to UTC, no business logic. | techrequest_index_bronze, tr_dossier_metadata_bronze, tr_messages_metadata_bronze, tr_manufacturing_quality_bronze, tr_linked_dossier_bronze. |
| Silver | Cleansed, joined, and conformed. Operator-ICAO patches applied via a reference table. RTS / Permanent-Request classifiers run here. Output one record per dossier_id with denormalized message and approval-doc aggregates. | ufo_entry_silver, ufo_message_silver, ufo_approval_doc_silver, ufo_post_treatment_silver, ufo_interruption_silver, ufo_linked_dossier_silver. |
| Gold (Ontology-backing) | Ontology-shaped, one dataset per object type. Incremental + APPEND with dossier_id (or composite) as primary key. | ufo_entry_gold → UfoEntry; ufo_message_gold → UfoMessage; ufo_approval_doc_gold → UfoApprovalDocument; ufo_post_treatment_gold → UfoPostTreatment; ufo_interruption_gold → UfoInterruption; ufo_mfg_quality_gold → UfoManufacturingQualityRfi. |

## 5.2 Ontology Surface — Objects, Interfaces, Links

Re-design the ontology around five focal object types plus supporting reference and link types. Adopt an Interface (TechRequestDossier) that captures the common identity surface — dossier_id, dossier_internal_id, operator_code_icao, aircraft_program — so UfoEntry, UfoApprovalDocument, UfoMessage, UfoPostTreatment, and UfoInterruption can share property contracts.

| Object Type | Primary Key | Notable Properties | Implements Interface |
| --- | --- | --- | --- |
| UfoEntry (V2) | dossier_id | dossier_title, dossier_label, dossier_status, operator_code_icao, aircraft_msn[], ata_chapter/ata, escalation flags, prioritization metadata, post-treatment summary fields. | TechRequestDossier |
| UfoMessage | message_id | dossier_id, message_type, message_sub_type, urgency, requested_answer_time, planned_answer_time, message_status, is_message_acknowledged. | TechRequestDossier |
| UfoApprovalDocument | approval_doc_id | dossier_id, approval_doc_type, category, limitation_type, rdaf_type, start_date, limitation_life_percent (computed). | TechRequestDossier |
| UfoPostTreatment (new) | dossier_id | post_treatment_status, _reason, sari_*, tdo_*, manufacturing_quality_*, environment_impact_*, isi_*, doc_content_*. | TechRequestDossier |
| UfoInterruption (new) | interruption_id (synthetic) | dossier_id, is_operational, is_technical, interruption_duration, interruption_type, symptom_code, departure_airport_iata, arrival_airport_iata, etops_edto. | TechRequestDossier |
| UfoManufacturingQualityRfi (new) | skywise_rfi_id | dossier_id, rfi_message_id, rfi_creation_time. | TechRequestDossier |
| UfoCompany (reference) | company_id (CWA/WA) | name, code_icao, code_cki, cage_code, category, country. | — |
| UfoFsr | fsr_uuid | name, last_log_in, current_log_in, watch_list, post_comment_flag. Favorites now via Link Type (see below). | — |
| UfoFsrTeam | operator_code_icao | name, action_log[Struct], fsrs[]. | — |
| UfoIcao | code_icao | open_count, closed_count, ambers_alloted, amber_count, red_count, caps. | — |
| UfoEscalation | escalation_uid | dossier_id, escalation_type, raised_date, user, icao. | — |
| PriorityAlgorithm | algorithm_id | params[Struct][], main_config_flag. | — |

### 5.2.1 Link Types

- UfoEntry ↔ UfoMessage (1-to-many): dossier_id → message.dossier_id.

- UfoEntry ↔ UfoApprovalDocument (1-to-many): dossier_id → approvalDoc.dossier_id.

- UfoEntry ↔ UfoPostTreatment (1-to-1).

- UfoEntry ↔ UfoInterruption (0-to-many).

- UfoEntry ↔ UfoManufacturingQualityRfi (0-to-many).

- UfoEntry ↔ UfoEntry (many-to-many, Linked Dossier) — properties: linked_type ∈ {Move, Copy} from tr_linked_dossier.

- UfoEntry ↔ UfoCompany (Requestor, many-to-1) and (VisibleBy, many-to-many).

- UfoFsr ↔ UfoEntry (Favorites, many-to-many) — replaces UfoFsr.favorites string array.

- UfoFsr ↔ UfoFsrTeam (many-to-1).

- UfoFsr ↔ UfoEscalation (1-to-many).

### 5.2.2 Struct Types

- CommentEntry (timestamp, author_uuid, author_display, code ∈ {Parts|Technical|Customer Support}, body, is_linked, linked_msn_ids[]).

- ActionLogEntry (fsr, timestamp, action, value) — replaces the stored-action delimited string.

- PriorityParameterConfig (name, is_span_parameter, tier_values[5]) — replaces the 10-way param1Config…param10Config branching.

## 5.3 Functions V2 Layout

Refactor UFO_OntologyObject_Functions into a modular Functions V2 repository. Each domain becomes its own file with a tightly-scoped export. Adopt OntologyEditFunction signatures with explicit Edits<>() types and async/await throughout.

| Module (V2) | Replaces | Public Surface |
| --- | --- | --- |
| prioritization/algorithm.ts | index.ts configureAlgorithm + findBounds + getPriorityValsForOneEntry + calculateGlobalScore + calculatePropertyScore + spanorBlock | scoreEntries(entries), scoreOneEntry(entry), scoreEntriesWithAlgorithm(entries, algo). Table-driven via PriorityParameterConfig structs. |
| fsr/edit.ts | fsrEntryDriver + setStoredFSREntry + executeStoredFSREntry | applyFsrEdit(entry, edit: FsrEditStruct), queueFsrEdit(entry, edit), flushQueuedEdits(team). |
| fsr/favorites.ts | FSRFunctions.scenarioFSRMatch + addAndupdateFSRFavs + removeAndupdateFSRFavs | Uses Link Type instead of string[] — addFavorites(fsr, entries), removeFavorites(fsr, entries). |
| fsr/identity.ts | FSRFunctions.scanandDelete + fsrTeam.setTeamMembers + Misc.commentFlag | scanInactiveFsrs(thresholdDays), refreshTeamMembers(team), toggleCommentFlag(fsrs). |
| comments/parse.ts + comments/write.ts + comments/views.ts | Comments.ts (entire file) | Strongly-typed CommentEntry struct; views: partsComments / techComments / customerSupportComments / linkedComments backed by a single dispatcher. |
| escalation/lifecycle.ts | escalate + deEscalate + createEscalationObject | raiseEscalation(entry, type, user), closeEscalation(entry, type), revertEscalation(entry, type). |
| icao/rollup.ts | calculateCountsforICAOS + updateClosed | rollupIcaoCounts(icaos, entries). |
| reporting/report.ts | reportGenerator.ts | buildEscalationDigest(team) → Notification, getRecentComments(team), summarizeActions(team). |
| dashboard/restoration.ts | restoration.ts | filterChange(...), unchanged signature for Workshop compatibility. |

# 6. Migration Phases

The migration is sequenced to land business value early (V2 ingest, immediate read-only parity) before re-platforming compute (incremental transforms) and surface (Functions V2 + ontology re-shape).

## 6.1 Phase Plan

| Phase | Theme | Key Deliverables | Exit Criteria |
| --- | --- | --- | --- |
| P0 | Stabilize | Lock branch, snapshot V1 ontology, freeze schema, install Functions V2 toolchain, enable validation builds. | Repos build green; baseline metrics captured (latency, cost per build, dashboard query SLO). |
| P1 | V2 Bronze ingest | Wire tr_dossier_metadata_filtered, tr_messages_metadata, tr_manufacturing_quality_reference, tr_linked_dossier, and techrequest_index_metadata_v2 into Bronze with TZ normalization. | Bronze datasets reconcile against V1 within agreed tolerance (row counts, key overlap). |
| P2 | Silver + parity | Re-implement existing UfoEntry / Message / ApprovalDoc / Path / Icao logic on V2 inputs using DataFrame APIs. Stand up reference-table for operator-ICAO patches. | Silver outputs match V1 outputs on a held-out sample to >99.5% on prioritization-relevant fields. |
| P3 | Ontology re-shape | Introduce TechRequestDossier interface; add UfoPostTreatment, UfoInterruption, UfoManufacturingQualityRfi, UfoCompany; new Link Types and Struct Types; migrate UfoFsr.favorites to a Link. | Ontology proposal merged; Workshop dashboards re-bound; existing actions remain green. |
| P4 | Functions V2 | Port prioritization, FSR edits, comments, escalations, reporting into modular Functions V2. Replace delimited strings with Struct types. | Function unit tests pass; @OntologyEditFunction edits roundtrip; ICAO rollups produce parity with V1. |
| P5 | Incrementality & scale | Switch Gold transforms to @incremental + APPEND with primary keys; partition by aircraft_program / operator_code_icao; tune Spark configs to V2 volumes. | Build cost ≤ 50% of V1 baseline on equivalent traffic; SLA on full-refresh + incremental hit budget. |
| P6 | Cutover & decommission | Dual-write window, dashboard cutover, V1 transform deprecation, V1 ontology fields archived. | V1 datasets quiesced; alerts move to V2 monitors; runbook handed off to Ops. |

## 6.2 Phase Dependencies

- P1 unblocks everything — until V2 lands in Bronze with consistent timestamps, downstream re-shaping is speculative.

- P3 (ontology) can run in parallel with P2 (silver parity) on a separate ontology branch, then merged once parity is signed off.

- P4 (Functions V2) depends on P3 — the new Struct types must exist before functions can be re-written to consume them.

- P5 (incrementality) requires the Silver/Gold split from P2 to have stabilized.

# 7. Risks & Mitigations

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Silent drift between V1 and V2 column semantics (e.g., timezones, MSN array nullability). | Wrong priority scores; broken FSR view. | High | Build a parity harness that joins V1 and V2 on dossier_id and asserts column-by-column equivalence over a rolling 90-day sample. Fail the build on drift. |
| Hardcoded RIDs across PySpark transforms. | Cutover requires touching every file. | High | Introduce a Foundry-properties config (yaml) referenced by all transforms via a thin wrapper. |
| Free-text RTS scraping misses V2 structured equivalents. | Loss of return-to-service signal. | Medium | Keep the scraper as a fallback, but prefer structured fields whenever V2 supplies them. Log fallback usage. |
| FSR Favorites migration from string[] to Link Type. | Lost favorites at cutover. | Medium | Migration script: read each UfoFsr.favorites, materialize Link Type rows, validate count, then null the column. |
| Functions V2 type changes (LocalDate, Timestamp ergonomics). | Compile errors during port. | Medium | Port one module at a time, behind a feature flag. Keep V1 functions running until V2 reaches parity. |
| Comment delimiters appearing in user content. | Comment parsing breaks for users typing '%*' or '.' | Low | Replace with structured Struct storage at the same time as Functions V2 port. Add unit tests for adversarial inputs. |
| Module-level mutable state in PySpark transforms (msnSeen, dossSeen*). | Wrong outputs under retries / incremental runs. | High | Move all aggregation into DataFrame group-by operations; eliminate driver-side dictionaries. |
| Ontology rename breaks Workshop dashboards. | User-visible outage. | Medium | Use Ontology property aliases during cutover; migrate widgets in batches; close out after final cutover. |

# 8. Documentation & Quality Gates

## 8.1 Documentation Surface

- API-style docs for every PySpark transform: inputs (RID + schema), outputs (RID + schema), invariants, idempotency, incremental semantics.

- API-style docs for every TypeScript function: parameters, return type, side-effects, complexity, ontology objects edited, idempotency, parallel-safety.

- Ontology reference: per object type, the property list, derived properties, base types, mandatory/required properties, link types, action types, and which interfaces it implements.

- Action-type catalog: parameter definitions, default values, validators, submission criteria, and the function they invoke.

- Runbook: build schedule, dependency DAG, manual-rerun procedure, parity-harness usage, V1 fallback toggle.

## 8.2 Quality Gates

- Static analysis: ruff / black for Python; eslint + strict TypeScript for TS; type checks on every PR.

- Unit tests for every prioritization branch (exact match, span, dates, keywords, escalations, TR-status).

- Integration tests for transforms: golden-output dataset checked into source control for a small sample.

- Parity harness as a scheduled job; alert on drift.

- Code review checklist: no driver-side collect(), no module-level mutable state, all timestamps UTC, all property accesses through the descriptor map.

## 8.3 Reference Material

- Palantir docs — Ontology: ontology overview, object & link types, structs & shared properties, value types, action types, interfaces (palantir.com/docs/foundry/ontology/* and /object-link-types/*).

- Palantir docs — Functions: functions overview, language-feature support, types reference, TypeScript V2 getting started, function actions, edits overview.

- Palantir docs — Architecture & Indexing: object backend, object permissioning, object indexing, object edits, object storage v1.

- UFO operator documentation: the PDFs under Documentation/ (Create Request, Internal Requestor, Analyse / Provide contribution, Approve Doc – RDAF / ASAC / FCD, Defect Report, Contribution RDTS / ASACAS / FCDAS / TDAW, Send Final Answer, Visibility & Visibility Management, UFO Part by Part).

# 9. Recommended Next Steps

To move from review to execution, propose the following concrete actions over the next two iterations.

- Confirm scope and phasing. Review §1 goals, §5 target architecture, and §6 phases with engineering and product. Capture any object-type additions that should be in-scope for P3.

- Stand up Bronze (Phase 1). Wire the five V2 source files into Bronze datasets with TZ normalization. This is the lowest-risk, highest-leverage first move.

- Write the parity harness. A small PySpark transform that compares V1 UfoEntry against V2-derived UfoEntry on the held-out sample. Use the dossier_internal_id (stable across versions) as the join key.

- Author the Ontology proposal. TechRequestDossier interface, new object types (PostTreatment, Interruption, ManufacturingQualityRfi, Company), and the linked-dossier Link Type.

- Spike Functions V2 on one module. Pick comments/ as the spike — small, well-bounded, and the highest beneficiary of Struct typing. Validate the dev loop before scheduling the rest.

- Decide the cutover envelope. Date and time of dual-write start, dashboard freeze window, V1 quiesce date.

End of review. Subsequent documents (Architecture Design, Ontology Design, Functions V2 Migration Plan, Transform Modernization Plan) will go deep on the items called out here.